## Slide 1: Planning
When you can measure what you are speaking about, and express it in numbers, you know something about it; but when you cannot measure it, when you cannot express it in numbers, your knowledge is of a meager and unsatisfactory kind.

## Slide 2: Initial Exploration:
At the start of the project, the developers and customers have conversations about the new system in order to identify all the significant features that they can.
However, they don't try to identify all features. As the project proceeds, the customers will continue to discover more features. The flow of features will not shut off until the project is over.
As a feature is identified, it is broken down into one or more user stories, which are written onto index cards or their equivalent.
Not much is written on the card except the name of the story (e.g., Login, Add User, Delete User, or Change Password).

## Slide 3: Contd…
The developers work together to estimate the stories. The estimates are relative, not absolute.
We write a number of "points" on a story card to represent the relative cost of the story.

## Slide 4: Spiking, Splitting, and Velocity
Stories that are too large or too small are difficult to estimate.
Developers tend to underestimate large stories and overestimate small ones.
Any story that is too big should be split into pieces that aren't too big.
Any story that is too small should be merged with other small stories.

## Slide 5: Case Study:
For example, consider the story "Users can securely transfer money into, out of, and between their accounts." This is a big story. Estimating will be difficult, and probably inaccurate.
However, we can split it into many stories that are much easier to estimate:
  Users can log in.
  Users can log out.
  Users can deposit money into their accounts.
  Users can withdraw money from their accounts.
  Users can transfer money from one of their accounts to another account.

## Slide 6: Contd…
When a story is split or merged, it should be re-estimated. It is not wise to simply add or subtract the estimate.
The whole reason to split or merge a story is to get it to a size at which estimation is accurate.
It is not surprising to find that a story estimated at 25 points breaks up into stories that add up to 30! Thirty is the more accurate estimate.
Every week, we complete a certain number of stories. The sum of the estimates of the completed stories is a metric known as velocity.
If we completed 42 points' worth of stories during the previous week, our velocity is 42.

## Slide 7: Contd…
After 3 or 4 weeks, we'll have a good idea of our average velocity. We can use this to predict how much work we'll get done in subsequent weeks.
Tracking velocity is one of the most important management tools in an XP project.
At the start of a project, the developers will not have a very good idea of their velocity. They must create an initial guess by whatever means they feel will give the best results.

## Slide 8: Release Planning:
Given a velocity, the customers can get an idea of the cost of each of the stories, as well as its business value and priority.
This allows the customers to choose the stories they want done first. This choice is not purely a matter of priority.
Something that is important but also expensive may be delayed in favor of something that is less important but much less expensive.
Choices like this are business decisions.
The developers and customers agree on a date for the first release of the project.

## Slide 9: Contd…
The customers pick the stories they want implemented within that release and the rough order they want them implemented in.
The customers cannot choose more stories than will fit according to the current velocity. Since the velocity is initially inaccurate, this selection is crude.
But accuracy is not very important at this point. The release plan can be adjusted as velocity becomes more accurate.

## Slide 10: Iteration Planning:
The developers and customers choose an iteration size: typically, 1 or 2 weeks.
Once again, the customers choose the stories that they want implemented in the first iteration but cannot choose more stories than will fit according to the current velocity.
The order of the stories within the iteration is a technical decision.
The developers implement the stories in the order that makes the most technical sense.
The customers cannot change the stories in the iteration once it has begun.
Customers are free to change or reorder any other story in the project but not the ones that the developers are currently working on.

## Slide 11: Defining "Done“:
A story is not done until all its acceptance tests pass. Those acceptance tests are automated.
They are written by the customer, business analysts, quality assurance specialists, testers, and even programmers, at the very start of each iteration.
These tests define the details of the stories and are the final authority on how the stories behave.

## Slide 12: Task Planning
At the start of a new iteration, the developers and customers get together to plan.
The developers break the stories down into development tasks. A task is something that one developer can implement in 416 hours.
The stories are analyzed, with the customers' help, and the tasks are enumerated as completely as possible.
A list of the tasks is created on a flip chart, whiteboard, or some other convenient medium.

## Slide 13: Contd…
Developers may sign up for any kind of task.
Database specialists are not constrained to sign up for database tasks. GUI people can sign up for database tasks if they like.
The benefit is obvious: The more the developers know about the whole project, the healthier and more informed the project team is.
We want knowledge of the project to spread throughout the team, irrespective of specialty.

## Slide 14: Contd…
Each developer knows how many task points he or she managed to implement in the previous iteration; this number is the developer's budget.
No one signs up for more points than are in the budget.
Task selection continues until either all tasks are assigned or all developers have used their budgets.
If tasks remain, the developers negotiate with each other, trading tasks, based on their various skills.

## Slide 15: Contd…
Half way through the iteration, the team holds a meeting. At this point, half of the stories scheduled for the iteration should be complete.
If half the stories aren't complete, the team tries to reapportion tasks and responsibilities to ensure that all the stories will be complete by the end of the iteration.

## Slide 16: Example
For example, suppose that the customers selected eight stories totaling 24 story points for the iteration.
Suppose also that these were broken down into 42 tasks. At the halfway point of the iteration, we would expect to have 21 tasks and 12 story points complete.
Those 12 story points must represent wholly completed stories. Our goal is to complete stories, not simply tasks.
The nightmare scenario is to get to the end of the iteration with 90 percent of the tasks complete but no stories complete.
At the halfway point, we want to see completed stories that represent half the story points for the iteration.

## Slide 17: Iterating
Every 2 weeks, the current iteration ends and the next begins.
At the end of each iteration, the current running executable is demonstrated to the customers.
The customers are asked to evaluate the look, feel, and performance of the project.
They will provide their feedback in terms of new user stories.

## Slide 18: Contd…
The customers see progress frequently. They can measure velocity.
They can predict how quickly the team is going and can schedule high-priority stories early.
In short, customers have all the data and control they need to manage the project to their liking.

## Slide 19: Tracking
Tracking and managing an XP project is a matter of recording the results of each iteration and then using those results to predict what will happen in the next iterations.
This chart shows how many story points were completed passed their automated acceptance tests at the end of each week.
Although there is some variation between the weeks, the data clearly shows that this team is completing around 42 story points per week.

## Slide 20: Contd…
This so-called burn-down chart shows, on a week-by-week basis, how many points remain to be completed for the next major milestone or release.
The slope of this chart is a reasonable predictor of the end date.

## Slide 21: Contd…
The difference between the bars in the burn-down chart does not equal the height of the bars in the velocity chart. The reason is that new stories are being added to the project.
It may also indicate that the developers have re-estimated the stories.
When these two charts are kept on the wall of the project room, anybody can look them over and tell within seconds what the status of the project is.
They can tell when the next major milestone will be met and to what degree the scope and estimates are creeping.
These two charts are the true bottom line for XP and all the agile methods. In the end, it's all about generating reliable management information.

## Slide 22: Conclusion
From iteration to iteration and release to release, the project falls into a predictable and comfortable rhythm. Everyone knows what to expect and when to expect it. Stakeholders see progress frequently and substantially.
Rather than being shown notebooks full of diagrams and plans, stakeholders are shown working software that they can touch, feel, and provide feedback on.
Developers see a reasonable plan, based on their own estimates and controlled by their own measured velocity.
Developers choose the tasks they feel comfortable working on and keep the quality of their workmanship high.

## Slide 23: Contd…
Managers receive data every iteration. They use this data to control and manage the project.
They don't have to resort to pressure, threats, or appeals to loyalty to meet an arbitrary and unrealistic date.
The stakeholders won't always be happy with the data that the process produces, especially not at first.
Using an agile method does not mean that the stakeholders will get what they want.
It simply means that they'll be able to control the team to get the most business value for the least cost.

## Slide 24: Thank you
Queries…..?????